## petasosexpress
PetasosExpress
Epic 1: Story 1: Creating an Initial App Build
Name | Subitems | Person | Status | Priority | Size | Timeline - Start | Timeline - End | Date of completion
Task 1: Prepare GitHub: Add Gitignore and README.md |  | Illia Popov, Dylan Ashton, William Margalik | Done | 🏕 Medium | 🐛 Miniscule | 2023-09-26 | 2023-09-27 | 2023-09-26
Task 2: Create empty layouts for the distance sensor, proximity sensor, balance sensor, and motor sensor screens |  | Dylan Ashton, William Margalik | Done | 🏕 Medium | 🦔 Tiny | 2023-09-26 | 2023-09-27 | 2023-09-27
Task 3: Add support for English and French languages |  | Ahmad Aljawish | Done | 🏕 Medium | 🐛 Miniscule | 2023-09-26 | 2023-09-27 | 2023-09-27
[6 empty] | 2023-09-26 | 2023-09-27 | 2023-09-26 to 2023-09-27
Epic 1: Story 2: Implement Navigation Drawer and Screen Design
Name | Subitems | Person | Status | Priority | Size | Timeline - Start | Timeline - End | Date of completion
Task 1: Integrate a navigation drawer into the app layout |  | Illia Popov | Done | 🏔 High | 🐂 Medium | 2023-09-27 | 2023-09-28 | 2023-09-27
Task 2: Define and structure navigation menu items |  | Illia Popov, William Margalik, Dylan Ashton | Done | 🏕 Medium | 🐇 Small |  |  | 2023-09-27
Task 3: Ensure smooth opening and closing of the drawer |  | Illia Popov, Ahmad Aljawish | Done | 🏕 Medium | 🐇 Small | 2023-09-27 | 2023-09-28 | 2023-09-27
[6 empty] | 2023-09-27 | 2023-09-28 | 2023-09-27
Epic 1: Story 3: Splash Screen and Loading Animation
Name | Subitems | Person | Status | Priority | Size | Timeline - Start | Timeline - End | Date of completion
Task 1: Design and implement a splash screen with the app logo |  | Illia Popov | Done | 🏕 Medium | 🐇 Small | 2023-09-27 | 2023-09-28 | 2023-09-27
Task 2: Add a description of the app to the screen |  | Ahmad Aljawish | Done | 🏕 Medium | 🐇 Small | 2023-09-27 | 2023-09-28 | 2023-09-27
Task 3: Implement a delay to display the splash screen briefly and transition to the main screen |  | William Margalik | Done | 🏕 Medium | 🐇 Small | 2023-09-27 | 2023-09-28 | 2023-09-27
[6 empty] | 2023-09-27 | 2023-09-28 | 2023-09-27
Epic 2: Story 1: Creating an UI for General Purpose Screens
Name | Subitems | Person | Status | Priority | Size | Timeline - Start | Timeline - End | Date of completion
Task 1: Creation of Login Screen UI (edit fields from usernameand password, button to login); |  | Illia Popov | Done | 🏔 High | 🐂 Medium | 2023-10-03 | 2023-10-05 | 2023-10-03
Task 2: Development of the Setting Screen UI (Should have at least 4 features) |  | Ahmad Aljawish | Done | 🏔 High | 🐂 Medium | 2023-10-03 | 2023-10-05 | 2023-10-03
Task 3: Home Fragment UI development |  | William Margalik | Done | 🏔 High | 🐂 Medium | 2023-10-03 | 2023-10-05 | 2023-10-05
Task 4: Splash Screen design fixes from feedback |  | Dylan Ashton | Done | 🏕 Medium | 🦔 Tiny | 2023-10-03 | 2023-10-05 | 2023-10-05
[6 empty] | 2023-10-03 | 2023-10-05 | 2023-10-03 to 2023-10-05
Epic 2: Story 2: Creating an UI for Sensor Screens
Name | Subitems | Person | Status | Priority | Size | Timeline - Start | Timeline - End | Date of completion
Task 1: Creating GPS sensor Screen UI (must include map to track the robot) |  | Illia Popov | Done | 🏕 Medium | 🐂 Medium | 2023-10-05 | 2023-10-06 | 2023-10-06
Task 2: Developing Distance Sensor Screen UI |  | Illia Popov | Done | 🏔 High | 🐂 Medium | 2023-10-05 | 2023-10-06 | 2023-10-05
Task 3: Designing the Proximity Sensor Screen UI |  | Dylan Ashton | Done | 🏔 High | 🐂 Medium | 2023-10-05 | 2023-10-06 | 2023-10-05
Task 4: Develop a detailed design for Balance Sensor Screen |  | Ahmad Aljawish | Done | 🏔 High | 🐂 Medium | 2023-10-05 | 2023-10-06 | 2023-10-05
Task 5: Create design for motors' sensor screen |  | William Margalik | Done | 🏔 High | 🐂 Medium | 2023-10-05 | 2023-10-06 | 2023-10-06
[6 empty] | 2023-10-05 | 2023-10-06 | 2023-10-05 to 2023-10-06
Epic 2: Story 3: Creating a landscape version of Screens UI
Name | Subitems | Person | Status | Priority | Size | Timeline - Start | Timeline - End | Date of completion
Task 1: Transferring Distance Sensor Screen UI to landscape format |  | Illia Popov | Done | 🏝 Low | 🐇 Small | 2023-10-06 | 2023-10-09 | 2023-10-09
Task 2: Redesign the UI of Proximity Sensor Screen for landscape |  | Dylan Ashton | Done | 🏝 Low | 🐇 Small | 2023-10-06 | 2023-10-09 | 2023-10-06
Task 3: Develop a detailed design for Balance Sensor Screen |  | Ahmad Aljawish | Done | 🏝 Low | 🐇 Small | 2023-10-06 | 2023-10-09 | 2023-10-09
Task 4: Create design for motors' sensor landscape screen |  | William Margalik | Done | 🏝 Low | 🐇 Small | 2023-10-06 | 2023-10-09 | 2023-10-09
Task 5: Develop Landscape version of Home screen |  | William Margalik | Done | 🏔 High | 🐇 Small | 2023-10-06 | 2023-10-09 | 2023-10-09
Task 6: Transfer Setting screen design to Landscape format |  | Ahmad Aljawish | Done | 🏕 Medium | 🐇 Small | 2023-10-06 | 2023-10-09 | 2023-10-09
Task 7: Creating Landscape variation of the Login Screen |  | Dylan Ashton | Done | 🏔 High | 🐇 Small | 2023-10-06 | 2023-10-09 | 2023-10-09
Task 8: Develop Splash Screen for Landscape orientation |  | Dylan Ashton | Done | 🏔 High | 🐇 Small | 2023-10-06 | 2023-10-09 | 2023-10-09
[6 empty] | 2023-10-06 | 2023-10-09 | 2023-10-06 to 2023-10-09
Epic 2: Story 4: Introducing a Firebase to the project and implementing authentication with its help
Name | Subitems | Person | Status | Priority | Size | Timeline - Start | Timeline - End | Date of completion
Task 1: Creating a Firebase Project and binding the Application to it |  | Illia Popov | Done | 🌋 Urgent | 🦔 Tiny | 2023-10-09 | 2023-10-10 | 2023-10-09
Task 2: Implement login screen functionality using FireBase Authentication database |  | Illia Popov | Done | 🏝 Low | 🐂 Medium | 2023-10-09 | 2023-10-10 | 2023-10-09
Task 3: Designing a Registration Screen UI |  | Illia Popov | Done | 🏕 Medium | 🐇 Small | 2023-10-09 | 2023-10-10 | 2023-10-09
Task 4: Implement registration process using FireBase |  | Illia Popov | Done | 🏝 Low | 🐂 Medium | 2023-10-09 | 2023-10-10 | 2023-10-09
[6 empty] | 2023-10-09 | 2023-10-10 | 2023-10-09
Epic 2: Story 5: Implementation of additional top menu options
Name | Subitems | Person | Status | Priority | Size | Timeline - Start | Timeline - End | Date of completion
Task 1: Adding the help option to the top menu to contact a call canter(requires permission) |  | Ahmad Aljawish | Done | 🏕 Medium | 🦔 Tiny | 2023-10-09 | 2023-10-10 | 2023-10-09
Task 2: Implement runtime permission for the Call Centre functionality |  | Ahmad Aljawish | Done | 🏕 Medium | 🐇 Small | 2023-10-09 | 2023-10-10 | 2023-10-09
Task 3: Adding the settings option that opens the settings screen |  | Ahmad Aljawish | Done | 🏕 Medium | 🦔 Tiny | 2023-10-09 | 2023-10-10 | 2023-10-09
Task 4: Adding the location option that opens the GPS sensor screen |  | Ahmad Aljawish | Done | 🏕 Medium | 🦔 Tiny | 2023-10-09 | 2023-10-10 | 2023-10-10
[6 empty] | 2023-10-09 | 2023-10-10 | 2023-10-09 to 2023-10-10